## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | Overview of the project(MediTrain AI-Empowering the Doctors of Tomorrow,Today) | MUST HAVE | No Dependencies | Mentor- 506 | 3- Completed
S1 | S1 | US-002 | Workflow Creation and Project Goal Document | MUST HAVE | Charts | Mentor-506 | 3- Completed
S2 | S2 | US-003 | Document Discussion(Agile Template,Defect Tracker,Unit Testing) | MUST HAVE | Excel sheets | Mentor-506 | 3- Completed
S2 | S2 | US-004 | Use Case Research and Preparation | SHOULD HAVE | W3School&Docs | Mentor-506 | 3- Completed
S3 | S3 | US-005 | Python practice Kit Completion | MUST HAVE | HackerRank | Mentor-506 | 3- Completed
S4 | S4 | US-006 | Langchain,Flask,prompts Kit Completion | MUST HAVE | Documentations | Mentor-506 | 3- Completed
S5 | S5 | US-007 | Project Discussion Module 1(Language Processing) | MUST HAVE | Groq API | Mentor-506 | 3- Completed
S6 | S6 | US-008 | Project Discussion Module 2(Workflow Efficiency ) | SHOULD HAVE | VS Code | Mentor-506 | 3- Completed
S7 | S7 | US-009 | Project Discussion Module 3(Merging existing services) | SHOULD HAVE | Langchain | Mentor-506 | 3- Completed
S8 | S8 | US-010 | Project Discussion Module 4(Testing and Deployment) | COULD HAVE | Render/streamlit | Mentor-506 | 3- Completed

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 61 | 18 | 14 | 11 | 10 | 4 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-001 | TID-01 | Overview of the project(MediTrain AI-Empowering the Doctors of Tomorrow,Today) | 2024-11-04 | 2024-11-06 |  | Others | 3- Completed | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | TID-02 | Workflow Creation and Project Goal Document | 2024-11-07 | 2024-11-08 |  | Design | 3- Completed | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | TID-03 | Document Discussion(Agile Template,Defect Tracker,Unit Testing) | 2024-11-11 | 2024-11-11 |  | Others | 3- Completed | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | TID-04 | Use Case Research and Preparation | 2024-11-12 | 2024-11-14 |  | Others | 3- Completed | 4 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | TID-05 | Python practice Kit Completion | 2024-11-16 | 2024-11-18 |  | Coding | 3- Completed | 5 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | TID-06 | Langchain,Flask,prompts Kit Completion | 2024-11-23 | 2024-11-27 |  | Coding | 3- Completed | 8 | 2 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | TID-07 | Project Discussion Module 1( Language Processing) | 2024-12-02 | 2024-12-05 |  | Build | 3- Completed | 10 | 2 | 2 | 2 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | TID-08 | Project Discussion Module 2(Workflow Efficiency ) | 2024-12-09 | 2024-12-14 |  | Coding | 3- Completed | 7 | 1 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | TID-09 | Project Discussion Module 3(Merging existing services) | 2024-12-15 | 2024-12-21 |  | Integration Test | 3- Completed | 11 | 3 | 2 | 2 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | TID-10 | Project Discussion Module 4(Testing and Deployment) | 2024-12-23 | 2024-12-28 |  | System Test | 3- Completed | 8 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 2 | Day 7 | Ambiguous User stories | Conducted a story grooming session
Sprint 3 | Day 13 | Difficulty in solving problems | Collaborated with mentor when stuck
Sprint 6 | Day 29 | Agile template confusion | Conducted a meeting where all doubts were clarified by the mentor.
Sprint 7 | Day 34 | Confusion in integration of LMS | Consulted with mentor to resolve the issue

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 3 | 2024-11-15 | 2024-11-22 |  |  | Delaying review of tasks | Maintaining focus on tasks | Achieved Python kit completion on time
2 | Sprint 7 | 2024-12-15 | 2024-12-20 |  |  | Using paid APIs | Exploring different LLMs | Found a LLM that will be great for the chatbot
3
4